## Sheet1
PBI | Tasks | Estimated Time | Assignee | Not started | In Progress | Completed | HRS | Task
PBI 1. MV algorithm | Create skeleton code | 30 min |  | TRUE | FALSE | FALSE | 3:15 | MV Algorithm
| Setup doxygen for each method | 15 min |  | TRUE | FALSE | FALSE | 1:45 | Entering CSV for MV
| Review election abstract class for refactoring | 15 min |  | TRUE | FALSE | FALSE | 2:30 | Read election type from CSV
| Design MV functions | 30 min |  | TRUE | FALSE | FALSE | 2:00 | 60% of ballots
| Implement MV functions | 30 min |  | TRUE | FALSE | FALSE | 0:45 | Display MV results
| Unit test creation | 45 min |  | TRUE | FALSE | FALSE | 1:40 | Report to user invalid ballots
| Integration test creation | 30 min |  | TRUE | FALSE | FALSE
|  | 3:15 |  |  |  |  | Total | 11:55
PBI 2. Entering CSV for MV | Review file handler for refactoring | 15 min |  | TRUE | FALSE | FALSE
| Refactor file handler to include MV | 15 min |  | TRUE | FALSE | FALSE
| Refactor Main to include case for MV | 15 min |  | TRUE | FALSE | FALSE
| Create MV test file | 15 min |  | TRUE | FALSE | FALSE
| Unit Test | 15 min |  | TRUE | FALSE | FALSE
| Integration test | 30 min |  | TRUE | FALSE | FALSE
1:45
PBI 3. Read election type from csv | Refactor main so that it is no longer prompting for vote type or seats | 15 min |  | TRUE | FALSE | FALSE
| Refactor file handler | 45 min |  | TRUE | FALSE | FALSE
| Unit test | 30 min |  | TRUE | FALSE | FALSE
| Integration test | 1 hour |  | TRUE | FALSE | FALSE
2:30
PBI 4. 60% of ballots must be ranked | Refactor File handler- read to ensure that all are ranked | 20 min |  | TRUE | FALSE | FALSE
| Refactor main- send error message to user if not enough ranked | 10 min |  | TRUE | FALSE | FALSE
| Unit test | 45 min |  | TRUE | FALSE | FALSE
| Integration test | 45 min |  | TRUE | FALSE | FALSE
2:00
PBI 5. Display MV results | Refactor MV to print out winners/results to screen | 15 min |  | TRUE | FALSE | FALSE
| Unit test | 15 min |  | TRUE | FALSE | FALSE
| Integration test | 15 min |  | TRUE | FALSE | FALSE
0:45
PBI 6. Report to user invalid ballots | Refactor file handler- display ballots that did not comply with 60% req | 20 min |  | TRUE | FALSE | FALSE
| Unit testing | 35 min |  | TRUE | FALSE | FALSE
| Integration testing | 45 min |  | TRUE | FALSE | FALSE
1:40
PBI Number | User Story | Acceptance Criteria | Definition of Done
RANKED
PBI 1 | As an election official I would like the option to run another type of voting algorithm called municipal voting (MV) So that the election official can satisfy the Secretary of State’s requirements | The election system must be able to recognize ‘MV’ on a file and conduct municipal voting Municipal voting must be conducted correctly and with no errors | The election system must be able to recognize ‘MV’ on a file and conduct municipal voting Municipal voting must be conducted correctly and with no errors
PBI 2 | As an election official I want to run municipal voting through entering a .csv So that the procedure to run an election is the same across all election types, and the complexity of running elections is reduced | Municipal voting elections can be run using file input, the same as all other election algorithms | File handler now recognizes “MV” in a .csv as municipal voting File handler properly parses the file into seats, candidates, and ballots (Like in PBI 1) Properly tested with no errors
PBI 3 | As an election official I want to only input a file name(s) and have the election run without any further input So that it is easier to run elections without human-made errors | Main only prompts the user for .csv file with election information The election algorithm that is specified in the file is run (STV or Plurality) The election is ran with the number of seats specified in the file | File handler chooses which election algorithm is run after reading from the file File handler determines how many seats are in the election after reading the file File handler is reading the ballots below election information Properly tested with no errors
PBI 4 | As an election official I want the system to ensure that 60% of candidates are ranked on an STV ballot So that STV has a sufficient number of ranked candidates. | Ballots that do not have enough candidates ranked are not used in stv election Removed ballots are listed in a file called STVBallotsErrorsXXXXXXXX where the x’s are replaced with the date the election was conducted STV must only be conducted with valid ballots | Functionality to read and process ranked STV ballots is implemented Logic is included to check if 60% or more ballots ranked for total candidates Testing conducted to verify code logic Documentation is complete
PBI 5 | As an election official I want to see the results of a municipal election (MV) printed on the screen So that I know what the result is of the election | After a municipal voting election is run, print the type of election After a municipal voting election is run, print the number of Seats After a municipal voting election is run, print the number of Files After a municipal voting election is run, print the number of Ballots After a municipal voting election is run, print the number of Votes Cast (number of 1s in the ballots) After a municipal voting election is run, print the list of Candidates with the stats of the election: number of votes received and the % of the overall number of votes received based on the total number of 1s in all of the ballots. After a municipal voting election is run, print the winner(s) of the election | Properly tested with no errors Municipal voting object stores, number of seats, files, ballots, votes cast, winners Municipal voting calculates and prints all statistics required in the acceptance criteria
PBI 6 | As an election official I want to be able to see the invalidated ballots of the STV election So that I can comply with the STV election rules and validate ballot regulations | The software checks if ballots are ranked 60% in STV The ballots invalid in STV are removed an included in a file called STVBallotErrorXXXXX where XXXXX is the date of the election Report lists each ballot that was removed from a ranking error | Report generation is completed correctly (including name, functionality, and content) Code is documented Properly tested with no errors
PBI 7 | As an election official After running the Municipal Voting system, I want an audit file to be generated. So that I can have a record of the MV results | MVElectionxxxxxxxx, where the xxxxxxxx represents the date of the election. The file should contain the information: Number of Seats Number of Files Number of Ballots Number of Votes Cast (number of 1s in the ballots) List of Candidates with the stats of the election: number of votes received and the % of the overall number of votes received based on the total number of 1s in all of the ballots. The winner(s) of the election | MVElectionxxxxxxxx, where the xxxxxxxx represents the date of the election. The file should contain the information: Number of Seats Number of Files Number of Ballots Number of Votes Cast (number of 1s in the ballots) List of Candidates with the stats of the election: number of votes received and the % of the overall number of votes received based on the total number of 1s in all of the ballots. The winner(s) of the election Appropriate documentation and testing has been done
UNRANKED
PBI 8 | As an election official I want to be able to click on my file to upload it, like I can with File Explorer on Windows So that it is easier for me to run an election | Able to click on files to import them into the system GUI system exists and functions on the user's screen | Able to click on files to import them, testing, and documentation has been done Code is tested and documented GUI is stable

## Sheet2
Task | Status | Owner | Stage | Due date | Notes
| Not started |  | Pre-event
| In progress |  | Day of
| Blocked |  | Post-event
Completed