## Sheet1
Sp | Tasks | Estimated Time | Assignee | Not started | In Progress | Completed | HRS | Task
PBI 1. MV algorithm | Create skeleton code | 30 min | Adam | FALSE | FALSE | TRUE | 3:15 | MV Algorithm
| Setup doxygen for each method | 15 min | Arish | FALSE | FALSE | TRUE | 1:30 | Entering CSV for MV
| Review election abstract class for refactoring | 15 min | Hlina | FALSE | FALSE | TRUE | 2:30 | Read election type from CSV
| Design MV functions | 30 min | Hlina | FALSE | FALSE | TRUE | 2:00 | 60% of ballots
| Implement MV functions | 30 min | Arish | FALSE | FALSE | TRUE | 0:45 | Display MV results
| Unit test creation | 45 min | Rahim | FALSE | FALSE | TRUE | 1:40 | Report to user invalid ballots
| Integration test creation | 30 min | Rahim | FALSE | FALSE | TRUE
|  | 3:15 |  |  |  |  | Total | 11:40
PBI 2. Entering CSV for MV | Review files for refactoring | 15 min | Adam | FALSE | FALSE | TRUE
| Refactor Main to include case for MV | 15 min | Adam | FALSE | FALSE | TRUE
| Create MV test file | 15 min | Arish | FALSE | FALSE | TRUE
| Unit Test | 15 min | Rahim | FALSE | FALSE | TRUE
| Integration test | 30 min | Hlina | FALSE | FALSE | TRUE
1:30
PBI 3. Read election type from csv | Refactor main so that it is no longer prompting for vote type or seats | 15 min | Adam | FALSE | FALSE | TRUE
| Refactor file handler | 45 min | Hlina | FALSE | FALSE | TRUE
| Unit test | 30 min | Arish | FALSE | FALSE | TRUE
| Integration test | 1 hour | Rahim | FALSE | FALSE | TRUE
2:30
PBI 4. 60% of ballots must be ranked
| Refactor main- send error message to user if not enough ranked | 30 min | Adam | FALSE | TRUE | FALSE
| Unit test | 45 min | Rahim | FALSE | TRUE | FALSE
| Integration test | 45 min | Arish | FALSE | TRUE | FALSE
2:00
PBI 5. Display MV results | Refactor MV to print out winners/results to screen | 15 min | Hlina | TRUE | FALSE | FALSE
| Unit test | 15 min |  | TRUE | FALSE | FALSE
| Integration test | 15 min |  | TRUE | FALSE | FALSE
0:45
PBI 6. Report to user invalid ballots | Refactor file handler- display ballots that did not comply with 60% req | 20 min |  | TRUE | FALSE | FALSE
| Unit testing | 35 min |  | TRUE | FALSE | FALSE
| Integration testing | 45 min |  | TRUE | FALSE | FALSE
1:40

## Sheet2
Task | Status | Owner | Stage | Due date | Notes
| Not started |  | Pre-event
| In progress |  | Day of
| Blocked |  | Post-event
Completed